Project Diamond

Field Briefing Note

2nd December 2022

| GENERAL | DETAILS | COMMENTS |
| --- | --- | --- |
| Project Details | Version valid since | 25th October 2022 |
|  | Opportunity number | 2931690 |
|  | Project Name | Diamond |
|  | Contact Person/Project owners | Akshay Halepaty/ Akshay.halepaty@iqvia.com Shubhankar Vartak/ shubhankar.vartak@iqvia.com Mayuresh Rane/ mrane2@in.imshealth.com Mandar Rane/ mandar.rane@iqvia.com |
|  | Project Lead | Akshay Halepaty |
|  | Date commissioned | 2nd December 2022 |
|  | Field Team | Shilpa Gupta/ shilpa.gupta@market-xcel.com Bhanu Dhingra/ bhanu.dhingra@market-xcel.com |

| Study Background | Client is launching 4 products, one of which is Mg+B6 combination for PMS cramps and migraine |
| --- | --- |
| Research Objectives | To understand the concept testing and price sensitivity for Mg+B6 |
| Target Respondent Profile | Gynaecologists |
| Key requirements | - Quotas should be followed to a 100%. No deviations will be accepted - Please have extra attention to these questions: Q2, Q6, Q8 and Q9 |
| Methodology/ Technique | Quantitative face to face CAPI Interviews |
| Study Stages | Finalization of Documents: 1st December 2022 Completion of Scripting: By 5th December 2022 Recruitments and Fieldwork: Start Date of Fieldwork: 3rd December 2022 End Date of Fieldwork: 18th December 2022 Raw Data Submission: 20th December 2022 |
| Test Location Sample Composition & Quota | As given at the end of the document |
| Materials required for fielding the study | Screener, Questionaries, Field Briefing Note (FBN), Status Update Sheet |
| Field Work Schedule | 3rd December 2022- 18th December 2022 |
| ADR Declaration | Signed by all team members, field team, moderators, and transcribers (Trained by Akshay Halepaty) |
| Key Questions Counter Questions for AE | HIGH PROBABILITY QUESTIONS - NA LOW PROBABILITY QUESTIONS - NA |
| Reporting Timelines | Within 12 hours of conducting the qualitative interview with the doctors |
| IQVIA India PI ADR Reporting Email IDs for Team and Subcontractors | Mail ID: DLI-IQVIA India- PI AE_1@iqvia.com Owner: Rubina Farooqui (owner) Akshay Halepaty/ Akshay.halepaty@iqvia.com, Shubhankar Vartak/ shubhankar.vartak@iqvia.com, Mayuresh Rane/ mrane2@in.imshealth.com and Mandar Rane/ mandar.rane@iqvia.com |
| Reconciliation | Once field work begins, you must conduct a reconciliation on monthly basis and at the end of the project on ADR reported to local PV department using the “PV Project Set-up_QC_Reporting Forms and Contact List May 2018”; or ‘client specific PV reconciliation form’ – Even when there is no ADR recorded during the month/ for the project. Reconciliation occurs once a month if the fieldwork is longer than 30 days. Client has the right to audit PV records to confirm compliance with applicable laws. A PV audit may be a documentary audit or otherwise, with client’s auditors or other individuals. Please ensure proper documentation, storage and archiving of related documents. |

SAMPLE SPREAD

| Project Diamond- Musex |  |
| --- | --- |
| GYNAECOLOGISTS |  |
| CITIES | SAMPLE |
| Delhi | 5 |
| Lucknow | 2 |
| Kolkata | 5 |
| Patna | 3 |
| Mumbai | 5 |
| Ahmedabad | 2 |
| Bangalore | 5 |
| Coimbatore | 3 |
| TOTAL | 30 |

THANK AND CLOSE