## EWN
EARLY WARNING NOTE | [6 empty] | Yes
|  |  | STG |  |  |  | No
|  |  | Go Survey | Select | Select | Select
|  |  | Others | PAPI | Consumer | Ad Hoc
Job Name | Clean |  |  | CAPI | Retailer | Track
Job Number | 20221283 |  |  | CAWI | Healthcare | Others
Research Executive | Sumeet |  |  | CATI | B2B
Data Collection Method | CATI |  |  |  | Auto
Type Of Interview | Consumer |  |  |  | Others
Type Of Study | Ad Hoc
Platfrom | Go Survey
Center | Total Sample Size-Consumer
Delhi/NCR | 50
Bangalore | 50
Chennai | 50
Hyderabad | 50
Mumbai | 50
Total | 250
Project Schedule
| Activity | Date
Detail
| Final Questionnaire:- | 2022-12-21
| Field Work Start Date | 2022-12-23
| Field Work End Date | 2022-12-30
| Test Link | 2022-12-21
| Analysis Plan | 2022-12-26
Interim Tables
| Final Id's /Data confirmation:- | 2023-01-02
| Final Tables | 2023-01-03
Other Information | No of Open ended
| SPSS Data Required | No
| Excel Data file Required | Yes
| Extra Analysis | Yes
Target/Quota | Users of UC- Those who have done home cleaning from urban company
Age- 21 yrs and above
SEC: A
Interviews to be done from the client's database