## Sheet1
CreatedBy | Name Of Created By | L1 (Direct Assigning To OM or Self and within team member by PMs) | L1 - Name | L2 (Only Needs To show if PM role is availeble at Location) | L2-Name | L3 (EIC in case OM assigning task to EIC) | L3 Name | L1Department | L1ReportingManager | L2ReportingManager | L3ReportingManager | Assigned | VoucherNo | PhName | ProjectName | Job | Location | Task Allocater Department | WBS | TaskMaster | Status | Open at (L1/L2/L3) | WBSRef | ProjectStartDate | ProjectEndDate | PSDate | PEDate | AEDate | ASDate | PDays | ActualDays | Dependencies | Executive Name (PCN initiator) | ExecutiveReportingManager (PCN initiator) | NoofTasks | noofclosetask | WithinSLA | OutsideSLA | ActivityClosedBy
MX2181 |  | MX303 |  |  |  | MX319 |  | Operations | Sanjay Kumar |  | Amrita Chowdhury | MX303,MX319 | PPL-2365/1 | Pre-Kickoff | Fianza | 20230774 | Kolkata | Client Servicing | 2365.1.1 | Allot an EIC | Close | closed | PPL-2365/1/2 | 08-08-2023 | 08-09-2023 | Jul 27 2023 12:00AM | Jul 28 2023 12:00AM | Jul 27 2023 8:50PM | Jul 27 2023 8:49PM | 2 | 0 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX303 |  |  |  | MX319 |  | Operations | Sanjay Kumar |  | Amrita Chowdhury | MX303,MX319 | PPL-2365/1 | Pre-Kickoff | Fianza | 20230774 | Kolkata | Client Servicing | 2365.1.4 | Field kit | Close | closed | PPL-2365/1/6 | 08-08-2023 | 08-09-2023 | Aug 9 2023 12:00AM | Aug 10 2023 12:00AM | Aug 9 2023 6:55PM | Aug 9 2023 6:54PM | 2 | 0 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX303 |  |  |  | MX319 |  | Operations | Sanjay Kumar |  | Amrita Chowdhury | MX303,MX319 | PPL-2365/1 | Field Work | Fianza | 20230774 | Kolkata | Client Servicing | 2365.4.1 | Status Update | Close | closed | PPL-2365/1/7 | 08-08-2023 | 08-09-2023 | Aug 9 2023 3:30AM | Aug 10 2023 12:00AM | Aug 9 2023 6:56PM | Aug 9 2023 6:55PM | 2 | 0 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX303 |  |  |  | MX319 |  | Operations | Sanjay Kumar |  | Amrita Chowdhury | MX303,MX319 | PPL-2365/1 | Field Work | Fianza | 20230774 | Kolkata | Client Servicing | 2365.4.10 | Status Update | Close | closed | PPL-2365/1/19 | 08-08-2023 | 08-09-2023 | Aug 9 2023 3:30AM | Aug 18 2023 12:00AM | Aug 9 2023 6:57PM | Aug 9 2023 6:56PM | 8 | 0 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX303 |  |  |  | MX319 |  | Operations | Sanjay Kumar |  | Amrita Chowdhury | MX303,MX319 | PPL-2365/1 | Field Work | Fianza | 20230774 | Kolkata | Client Servicing | 2365.4.13 | Status Update | Close | closed | PPL-2365/1/22 | 08-08-2023 | 08-09-2023 | Aug 9 2023 3:30AM | Aug 21 2023 12:00AM | Aug 9 2023 6:58PM | Aug 9 2023 6:57PM | 9 | 0 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX303 |  |  |  | MX319 |  | Operations | Sanjay Kumar |  | Amrita Chowdhury | MX303,MX319 | PPL-2365/1 | Field Work | Fianza | 20230774 | Kolkata | Client Servicing | 2365.4.16 | Status Update | Close | closed | PPL-2365/1/25 | 08-08-2023 | 08-09-2023 | Aug 9 2023 3:30AM | Aug 22 2023 12:00AM | Aug 9 2023 6:59PM | Aug 9 2023 6:59PM | 10 | 0 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX303 |  |  |  | MX319 |  | Operations | Sanjay Kumar |  | Amrita Chowdhury | MX303,MX319 | PPL-2365/1 | Field Work | Fianza | 20230774 | Kolkata | Client Servicing | 2365.4.19 | Raw data download and sharing | Close | closed | PPL-2365/1/28 | 08-08-2023 | 08-09-2023 | Aug 11 2023 12:00AM | Aug 12 2023 12:00AM | Aug 11 2023 6:37PM | Aug 11 2023 6:37PM | 1 | 0 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX303 |  |  |  | MX319 |  | Operations | Sanjay Kumar |  | Amrita Chowdhury | MX303,MX319 | PPL-2365/1 | Field Work | Fianza | 20230774 | Kolkata | Client Servicing | 2365.4.22 | Raw data download and sharing | Close | closed | PPL-2365/1/31 | 08-08-2023 | 08-09-2023 | Aug 16 2023 5:23PM | Aug 16 2023 5:23PM | Aug 16 2023 9:26PM | Aug 16 2023 9:25PM | 1 | 0 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX303 |  |  |  | MX319 |  | Operations | Sanjay Kumar |  | Amrita Chowdhury | MX303,MX319 | PPL-2365/1 | Field Work | Fianza | 20230774 | Kolkata | Client Servicing | 2365.4.4 | Status Update | Close | closed | PPL-2365/1/13 | 08-08-2023 | 08-09-2023 | Aug 9 2023 3:30AM | Aug 14 2023 12:00AM | Aug 9 2023 7:01PM | Aug 9 2023 7:00PM | 4 | 0 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX303 |  |  |  | MX319 |  | Operations | Sanjay Kumar |  | Amrita Chowdhury | MX303,MX319 | PPL-2365/1 | Field Work | Fianza | 20230774 | Kolkata | Client Servicing | 2365.4.7 | Status Update | Close | closed | PPL-2365/1/16 | 08-08-2023 | 08-09-2023 | Aug 9 2023 3:30AM | Aug 16 2023 12:00AM | Aug 9 2023 7:02PM | Aug 9 2023 7:01PM | 6 | 0 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX2175 |  |  |  | MX344 |  | Data Management | Anil Kaul |  | Bibhu Prasad Pal | MX025,MX1470,MX1964,MX2175,MX344 | PPL-2365/1 | Data Processing | Fianza | 20230774 | Delhi 2 | Client Servicing | 2365.3.2 | Clean Data Required | Close | closed | PPL-2365/1/6 | 08-08-2023 | 08-09-2023 | Aug 17 2023 2:22PM | Aug 27 2023 12:00AM | Aug 22 2023 2:50PM | Aug 22 2023 2:50PM | 7 | 0 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX2175 |  |  |  | MX344 |  | Data Management | Anil Kaul |  | Bibhu Prasad Pal | MX025,MX1470,MX1964,MX2175,MX344 | PPL-2365/1 | Data Processing | Fianza | 20230774 | Delhi 2 | Client Servicing | 2365.3.3 | Clean Data Required | Close | closed | PPL-2365/1/6 | 08-08-2023 | 08-09-2023 | Aug 22 2023 3:05PM | Aug 22 2023 3:05PM | Aug 22 2023 2:50PM | Aug 22 2023 2:50PM | 1 | 0 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX2175 |  |  |  | MX344 |  | Data Management | Anil Kaul |  | Bibhu Prasad Pal | MX025,MX1470,MX1964,MX2175,MX344 | PPL-2365/1 | Data Processing | Fianza | 20230774 | Delhi 2 | Client Servicing | 2365.3.4 | Clean Data Required | Close | closed | PPL-2365/1/36 | 08-08-2023 | 08-09-2023 | Aug 22 2023 3:05PM | Aug 23 2023 12:00AM | Aug 23 2023 4:44PM | Aug 22 2023 3:44PM | 2 | 2 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX2175 |  |  |  | MX344 |  | Data Management | Anil Kaul |  | Bibhu Prasad Pal | MX1964,MX2175,MX344 | PPL-2365/1 | Data Processing | Fianza | 20230774 | Delhi 3 | Client Servicing | 2365.3.1 | Clean Data Required | Close | closed | PPL-2365/1/6 | 08-08-2023 | 08-09-2023 | Aug 9 2023 3:30AM | Aug 27 2023 12:00AM | Aug 22 2023 2:50PM | Aug 22 2023 2:50PM | 13 | 0 |  | MX2181 | MX461 | 1 | 1 | 1 | 0
MX2181 |  | MX2175 |  |  |  | MX344 |  | Data Management | Anil Kaul |  | Bibhu Prasad Pal | MX025,MX1470,MX1964,MX2175,MX344 | PPL-2365/1 | Data Processing | Fianza | 20230774 | Delhi 2 | Client Servicing | 2365.3.5 | Clean Data Required | Open | L3 | PPL-2365/1/37 | 08-08-2023 | 08-09-2023 | Aug 25 2023 12:00AM | Sep 2 2023 12:00AM |  |  | 6 |  |  | MX2181 | MX461 | 1 | 0 | 0 | 0
MX2181 |  | MX2175 |  |  |  | MX344 |  | Data Management | Anil Kaul |  | Bibhu Prasad Pal | MX1964,MX2175,MX344 | PPL-2365/1 | Questionnaire programming-Phase | Fianza | 20230774 | Delhi 3 | Client Servicing | 2365.2 | Allot an EIC | Close | closed | PPL-2365/1/5 | 08-08-2023 | 08-09-2023 | Jul 27 2023 12:00AM | Jul 30 2023 12:00AM | Jul 27 2023 6:09PM | Jul 27 2023 1:48PM | 2 | 1 |  | MX2181 | MX461 | 1 | 1 | 1 | 0