## FiNal Sample
27
Zone​ | States​ | District covered in old study (there will be addition as per the no of disrticts) | Paddy​ | Paddy​ | Cotton​ | Cotton​ | Soybean​ | Soybean​ | Pulses​ | Pulses​ | Wheat​ | Wheat​ | Grapes​ | Grapes​ | Potato​ | Potato​ | Chilly​ | Chilly​ | F&V​ | F&V​ | Gnut​ | Gnut​ | Total​ | Chhanel​ SS PD​ | Retailers​ | Grand Total​ | NO of Channel Partners DB received | Number of locations | Team Number | FW Start | FW End | Number of interviewers | Number of Tabs required
|  |  | Rallis User | Rallis Non User | Rallis User | Rallis Non User | Rallis User | Rallis Non User | Rallis User | Rallis Non User | Rallis User | Rallis Non User | Rallis User | Rallis Non User | Rallis User | Rallis Non User | Rallis User | Rallis Non User | Rallis User | Rallis Non User | Rallis User | Rallis Non User
South​ | Andhra Pradesh​ | Andhra Pradesh | 30 | 20 | 30 | 20 | ​ |  | ​ |  | ​ |  | ​ |  | ​ |  | 30 | 20 | 24 | 16 | ​ |  | 190​ | 20​ | 25​ | 235​
| Andhra Pradesh​ | East Godavari | 10 | 5 | [14 empty] | 5 | 4 |  |  | 24 | 2 |  |  | 11 | 8 | 1+2 | 2023-02-10 | 2023-02-11 | 4
| Andhra Pradesh​ | West Godavari | 10 | 5 | [14 empty] | 5 | 4 |  |  | 5 | 1 |  |  | 2 | 2 | 1+4 |  |  | 4
| Andhra Pradesh​ | Nellore | 5 | 5 | [18 empty] | 10 | 1 |  |  | 8 | 8 | 1+2 | 2023-02-16 | 2023-02-16 | 4
| Andhra Pradesh​ | Guntur |  |  | 5 | 5 | [10 empty] | 10 | 5 |  |  |  |  | 25 | 3 |  |  | 15 | 15 | 1+4 | 2023-02-10 | 2023-02-12 | 4
| Andhra Pradesh​ | Kurnool |  |  | 10 | 5 | [10 empty] | 5 | 5 |  |  |  |  | 25 | 3 |  |  | 20 | 17 | 1+2 | 2023-02-12 | 2023-02-14 | 4
| Andhra Pradesh​ | Anantapur |  |  | 10 | 5 | [16 empty] | 15 | 3 |  |  | 15 | 12 | 1+2 | 2023-02-15 | 2023-02-16 | 4
| Andhra Pradesh​ | Prakasam |  |  | 5 | 5 | [10 empty] | 5 | 5 | 5 | 3 |  |  | 28 | 2 |  |  | 11 | 9 | 1+4 | 2023-02-13 | 2023-02-15 | 4
| Andhra Pradesh​ | Krishna | 5 | 5 | [12 empty] | 10 | 5 | 5 | 3 |  |  | 33 | 4 |  |  | 6 | 6 | 1+4 | 2023-02-05 | 2023-02-09 | 4
| Andhra Pradesh​ | Madanapalle (Chittoor) | [16 empty] | 4 | 2 |  |  | 6 | 1 |  |  | 7 | 7 | 1+4 |  |  | 4
| Telengana​ | Telengana​ | 30 | 20 | ​ |  | 30 | 20 | 30 | 20 | ​ |  | ​ |  | ​ |  | 24 | 16 | ​ |  | ​ |  | 190​ | 20​ | 25​ | 235​
| Telengana​ | Nalgonda | 5 | 3 | [12 empty] | 5 | 3 |  |  |  |  | 25 | 1 |  |  | 6 | 6 | 1+4 | 2023-02-10 | 2023-02-11 | 4
| Telengana​ | Suryapet | 5 | 3 |  |  | 5 | 3 | [8 empty] | 5 | 3 |  |  |  |  | 16 | 2 |  |  | 1 | 1 |  |  |  | 4
| Telengana​ | Yadadri |  |  |  |  | 5 | 3 | [14 empty] | 8 | 1 |  |  | 1 | 1 |  |  |  | 4
| Telengana​ | Bhuvanagiri | [6 empty] | 5 | 4 | [12 empty] | 9 | 1 |  |  |  |  | 1+4 | 2023-02-12 | 2023-02-12 | 4
| Telengana​ | Nizamabad | 5 | 4 |  |  | 5 | 4 | [14 empty] | 18 | 2 |  |  | 5 | 5 | 1+4 | 2023-02-13 | 2023-02-16 | 4
| Telengana​ | Karimnagar | 5 | 4 |  |  | 5 | 4 | 5 | 4 | [6 empty] | 5 | 4 |  |  |  |  | 35 | 3 |  |  | 3 | 3 | 1+4 | 2023-02-10 | 2023-02-12 | 4
| Telengana​ | Adilabad | [20 empty] | 14 | 2 |  |  | 2 | 2 | 1+4 | 2023-02-13 | 2023-02-13 | 4
| Telengana​ | Kurnool | [20 empty] | not in Telagana | [5 empty] | Not Telangana State
| Telengana​ | Warangal | 5 | 3 |  |  |  |  | 5 | 4 | [6 empty] | 5 | 4 |  |  |  |  | 34 | 3 |  |  | 7 | 7 | 1+4 | 2023-02-06 | 2023-02-09 | 4
| Telengana​ | Khammam | [6 empty] | 5 | 4 | [6 empty] | 4 | 2 |  |  |  |  | 25 | 2 |  |  | 7 | 7 | 1+4 | 2023-02-14 | 2023-02-15 | 4
| Telengana​ | Bhadrachalam (Kothagudem) | 5 | 3 |  |  | 5 | 3 | [14 empty] | 16 | 2 |  |  | 3 | 3 | 1+4 | 2023-02-16 | 2023-02-16 | 4
| Telengana​ | Rangareddy |  |  |  |  | 5 | 3 | 10 | 4 | [12 empty] | 8 | 1 |  |  | 2 | 2 | 1+4 | 2023-02-03 | 2023-02-04 | 4
| Karnataka​ | Karnataka​ | 30 | 20 | ​ |  | 24 | 16 | 30 | 20 | ​ |  | 27 | 18 | ​ |  | ​ |  | 24 | 16 | ​ |  | 225​ | 20​ | 30​ | 275​
| Karnataka​ | Gangavathi (Koppal) | 4 | 2 |  |  |  |  | 4 | 2 |  |  | 4 | 3 |  |  |  |  | 2 | 2 |  |  | 23 | 3 | 3 | 29 | 13 | 7 | 1 | 2023-02-08 | 2023-02-10 | 2
| Karnataka​ | Sindhanur (Raichur) | 4 | 2 |  |  |  |  | 4 | 2 | [8 empty] | 2 | 2 |  |  | 16 | 1 | 3 | 20 | 1 | 1 | 1 | 2023-02-11 | 2023-02-14 | 2
| Karnataka​ | Davangere | 4 | 2 | [14 empty] | 2 | 2 |  |  | 10 | 3 | 3 | 15 | 13 | 10 | 2 | 2023-01-31 | 2023-02-02 | 2
| Karnataka​ | Belgaum | 2 | 2 |  |  | 10 | 6 | 4 | 3 |  |  | 4 | 2 |  |  |  |  | 2 | 2 |  |  | 37 | 2 | 3 | 42 | 5 | 5 | 2 | 2023-02-07 | 2023-02-10 | 2
| Karnataka​ | Hubli | 2 | 2 |  |  | 10 | 6 | 4 | 3 | [8 empty] | 2 | 1 |  |  | 30 | 1 | 3 | 35 | 1 | 1 | 2 | 2023-02-03 | 2023-02-06 | 2
| Karnataka​ | Gulbarga | 2 | 2 |  |  |  |  | 4 | 3 |  |  | 4 | 2 |  |  |  |  | 2 | 1 |  |  | 20 | 4 | 3 | 27 | 5 | 3 | 1 | 2023-02-05 | 2023-02-07 | 2
| Karnataka​ | shahapur (yadgir) | [6 empty] | 4 | 3 | [8 empty] | 2 | 1 |  |  | 10 | 0 | 2 | 12 | 0 | 0 | 1 | 2023-02-03 | 2023-02-04 | 2
| Karnataka​ | Chickballapur | [10 empty] | 3 | 3 |  |  |  |  | 2 | 1 |  |  | 9 | 1 | 2 | 12 | 3 | 1 | 2 | 2023-02-13 | 2023-02-16 | 2
| Karnataka​ | Bijapur | 3 | 2 | [8 empty] | 4 | 2 |  |  |  |  | 2 | 1 |  |  | 14 | 2 | 2 | 18 | 6 | 4 | 1 | 2023-02-13 | 2023-02-16 | 2
| Karnataka​ | Bagalkot | 3 | 2 |  |  | 4 | 4 | 3 | 2 |  |  | 4 | 3 |  |  |  |  | 2 | 1 |  |  | 28 | 2 | 2 | 32 | 12 | 8 | 1 | 2023-02-12 | 2023-02-16 | 2
| Karnataka​ | Kolar | 3 | 2 | [8 empty] | 4 | 3 |  |  |  |  | 2 | 1 |  |  | 15 | 1 | 2 | 18 | 4 | 4 | 2 | 2023-02-14 | 2023-02-16 | 2
| Karnataka​ | Chitradurga | 3 | 2 |  |  |  |  | 3 | 2 | [8 empty] | 2 | 1 |  |  | 13 | 0 | 2 | 16 | 0 | 0 | 2 | 2023-02-11 | 2023-02-14 | 2
| Kerala​ | Kerala​ | 24 | 16 | ​ |  | ​ |  | ​ |  | ​ |  | ​ |  | ​ |  | ​ |  | 24 | 16 | ​ |  | 80​ | 15​ | 20​ | 115​
| Kerala​ | Kottayam | 12 | 8 | [14 empty] | 12 | 8 |  |  | 40 | 6 | 10 | 56 | 6 | 6 | 1 | 2023-01-31 | 2023-02-10 | 2
| Kerala​ | Thrissur | 12 | 8 | [14 empty] | 12 | 8 |  |  | 40 | 0 | 10 | 50 | 0 | 0 | 1 | 2023-02-11 | 2023-02-16 | 2
| Total ​ |  | 240​ |  | 50​ |  | 90​ |  | 140​ |  | ​ |  | 45​ |  | ​ |  | 90​ |  | 160​ |  | ​ |  | 815​ | 95​ | 130​ | 1040​
North​ | Punjab​ | Punjab​ | 36 | 24 | 30 | 20 | ​ |  | ​ |  | 30 | 20 | ​ |  | ​ |  | ​ |  | ​ |  | ​ |  | 160​ | 20​ | 30​ | 210​
| Punjab​ | Sangrur | 6 | 4 | 0 | 0 |  |  |  |  | 5 | 4 | [10 empty] | 19 | 5 | 5 | 29 | 7 | 7 | 1 | 2023-01-15 | 2023-01-15 | 4
| Punjab​ | Moga | 6 | 4 | 0 | 0 |  |  |  |  | 5 | 3 | [10 empty] | 18 | 2 | 5 | 25 | 3 | 3 | 1 | 2023-01-13 | 2023-01-14 | 4
| Punjab​ | Barnala | 6 | 4 | 6 | 4 |  |  |  |  | 5 | 3 | [10 empty] | 28 | 2 | 4 | 34 | 3 | 3 | 1 | 2023-01-10 | 2023-01-12 | 4
| Punjab​ | Abohar | 6 | 4 | 12 | 8 |  |  |  |  | 5 | 3 | [10 empty] | 38 | 1 | 3 | 42 | 1 | 1 | 1 | 2023-01-04 | 2023-01-06 | 4
| Punjab​ | Muktsar (Malout) | 6 | 4 | 12 | 8 |  |  |  |  | 5 | 3 | [10 empty] | 38 | 4 | 5 | 47 | 5 | 5 | 1 | 2023-01-07 | 2023-01-09 | 4
| Punjab​ | Amritsar | 6 | 4 | 0 | 0 |  |  |  |  | 5 | 4 | [10 empty] | 19 | 6 | 8 | 33 | 8 | 8 | 1 | 2023-01-01 | 2023-01-03 | 4
| Uttar Pradesh​ | Uttar Pradesh​ | 30 | 20 | ​ |  | ​ |  | ​ |  | 30 | 20 | ​ |  | 30 | 20 | ​ |  | ​ |  | ​ |  | 150​ | 20​ | 25​ | 195​
| Uttar Pradesh​ | Udhamsingh nagar | 4 | 3 | [6 empty] | 4 | 3 |  |  | 4 | 3 | [8 empty] | 2 |  |  |  |  | 2023-01-16 | 2023-01-16 | 3+1
| Uttar Pradesh​ | Aligarh | 4 | 3 | [6 empty] | 4 | 3 |  |  | 4 | 3 | [8 empty] | 3 |  |  |  |  | 2023-01-15 | 2023-01-15 | 3+1
| Uttar Pradesh​ | Siddharth nagar | 6 | 4 | [6 empty] | 6 | 4 |  |  | 6 | 4 | [7 empty] | 3 | 3 |  | 3 | 3 |  | 2023-02-06 | 2023-02-09 | 3+1
| Uttar Pradesh​ | Barabanki | 8 | 6 | [6 empty] | 8 | 6 |  |  | 8 | 6 | [8 empty] | 3 |  |  |  |  | 2023-02-02 | 2023-02-05 | 3+1
| Uttar Pradesh​ | Hathras | 4 | 2 | [6 empty] | 4 | 2 |  |  | 4 | 2 | [7 empty] | 3 | 6 |  | 3 | 3 |  | 2023-02-13 | 2023-02-14 | 3+1
| Uttar Pradesh​ | Agra | 4 | 2 | [6 empty] | 4 | 2 |  |  | 4 | 2 | [7 empty] | 11 | 8 |  | 11 | 11 |  | 2023-01-10 | 2023-02-12 | 3+1
East​ | West Bengal & Assam ​ | West Bengal & Assam ​ | 36 | 24 | ​ |  | ​ |  | ​ |  | ​ |  | ​ |  | 30 | 20 | ​ |  | 24 | 16 | ​ |  | 150​ | 20​ | 30​ | 200​
| West Bengal & Assam ​ | Guwahati | 4 | 3 | [10 empty] | 5 | 5 |  |  | 3 | 2 |  |  | 22 |  |  | 22 | 0 | 0 | Team 1 | 2023-05-02 | 2023-06-02 | 2
| West Bengal & Assam ​ | Burdwan I | 6 | 3 | [10 empty] | 8 | 5 |  |  | 3 | 2 |  |  | 27 | 7 | 10 | 44 | 12 | 12 | Team2 | 2023-04-02 | 2023-07-02 | 4
| West Bengal & Assam ​ | Burdwan II | 6 | 3 | [10 empty] | 7 | 5 |  |  | 3 | 2 |  |  | 26 | 1 | 2 | 29 | 2 | 2 | Team2 | 2023-08-02 | 2023-09-02 | 4
| West Bengal & Assam ​ | Kharagpur (West Medinipur) | 4 | 3 | [14 empty] | 3 | 2 |  |  | 12 | 3 | 5 | 20 | 6 | 6 | Team2 | 2023-12-02 | 13/2/2023 | 4
| West Bengal & Assam ​ | Tarakeswar (Hooghly) | 4 | 3 | [10 empty] | 10 | 5 |  |  | 3 | 2 |  |  | 27 | 2 | 3 | 32 | 4 | 4 | Team2 | 2023-10-02 | 2023-11-02 | 4
| West Bengal & Assam ​ | Cooch behar | 0 | 0 | [22 empty] | 0 | 0
| West Bengal & Assam ​ | Amtala (Murshidabad) | 4 | 3 | [14 empty] | 3 | 2 |  |  | 12 | 2 | 3 | 17 | 4 | 4 | Team 1 | 2023-09-02 | 2023-10-02 | 2
| West Bengal & Assam ​ | Barasat (North 24 Parganas) | 4 | 3 | [14 empty] | 3 | 2 |  |  | 12 | 2 | 3 | 17 | 4 | 4 | Team1 | 2023-11-02 | 2023-12-02 | 2
| West Bengal & Assam ​ | Malda | 4 | 3 | [14 empty] | 3 | 2 |  |  | 12 | 3 | 4 | 19 | 6 | 6 | Team 1 | 2023-07-02 | 2023-08-02 | 2
| Orissa​ | Orissa​ | 30 | 20 | ​ |  | ​ |  | ​ |  | ​ |  | ​ |  | ​ |  | ​ |  | 24 | 16 | ​ |  | 90​ | 15​ | 20​ | 125​
| Orissa​ | Balasore | 10 | 8 | [14 empty] | 8 | 6 |  |  | 32 |  | 8 | 40 | 0 | 0 |  | 2023-12-02 | 15/2/2023 | 4
| Orissa​ | Bhadra | 10 | 7 | [14 empty] | 8 | 5 |  |  | 30 |  | 7 | 37 | 0 | 0 |  | 2023-03-02 | 2023-09-02 | 2
| Orissa​ | Khujan | 10 | 5 | [14 empty] | 8 | 5 |  |  | 28 |  | 7 | 35 | 0 | 0 |  | 2023-10-02 | 16/2/2023 | 2
| Total ​ |  | 165​ |  | 0​ |  | 0​ |  | 0​ |  | 0​ |  | 0​ |  | 50​ |  | 0​ |  | 120​ |  | 0​ |  | 335​ | 50​ | 70​ | 455​
Grand Total​ |  |  | 565​ |  | 265​ |  | 260​ |  | 295​ |  | 215​ |  | 110​ |  | 140​ |  | 140​ |  | 360​ |  | 110​ |  | 2460​ | 290​ | 400​ | 3150​

## FW Plan
State | Field Office | Sample | Date of FW Start | Date of FW Completion | Team Size using | No of Districts
AP | Hyderabad | 235 | 4.2.2023 | 20.2.2023 | 1+4 | 9
TL | Hyderabad | 235 | 3.2.2023 | 20.2.2023 | 1+4 | 12
KL | Cochin | 115 | 31.1.2023 | 20.2.2023 | 2+1 | 2
KAR | Bangalore | 275 | 2.2.2023 | 20.2.2023 | 4+1 | 12
PUN | Ludhiana | 210 | 2.2.2023 | 20.2.2023 | 4+1 | 6
UP | Lucknow | 195 | 2.2.2023 | 20.2.2023 | 4+1 | 6
WB & ASM | Kolkata | 200 | 4.2.2023 | 20.2.2023 | 6+2 | 9
ODI | Kolkata | 125 | 4.2.2023 | 20.2.2023 | 3+1 | 3