## List questoin QC manual
Ownership | Project Planning | Deployment
PM/Res | Project Name | IRIS 2.0
PM/Res | Job # | 20221111
PM/Res | Account Executive Name, email, mobile# | Bhanu Dhingra, bhanu.dhingra@market-xcel.com 7011743058
Ops | EIC Name, email, mobile#
PM/Res | Project Type | Quant
PM/Res | Centers
PM/Res | Audio recording needs be done (Y/N) | No
Ops | Team Size (Supervisor) (At each Center)
Ops | Team Size (interviewers) (At each Center)
Ops | Team Size (Audio checkers) (At each Center)
Ops | Productivity Assumption
PM/Res | Briefing Date (PM/Res to EIC) | 1.11.2022
Ops | Briefing Date (EIC to Sup & Int)
Ops | Mocks Assessment (Yes/No)
Ops | FW Launch Date
Ops | FW End Date
PM/Res/Ops | What all stages do we have in the study and who will be accountable for what stage at what level? | EWN, Briefing, Budget, Sharing update to cleint after getting the same from the team & Final budget closure
Ops | incase a facility is required for the study who will be accountable for ensuring that booked facility meets all the requriment required for the study?
Ops | who will be responsible for study schedule?
Ops | by when study schedule will made?
Ops | who will make data delivery plan?
PM/Res | Who will be responsible for Briefing to EIC's | PM
Ops | Who will be responsible for briefing to Sup & Interviewers
Ops | Who will be taking mocks sessions
Ops | How many accompaniments will done by supervisor? (Percentage)
Ops | How many accompaniments will done by EIC? (Percentage)
Ops | How many personal checks will be done by supervisor? (Percentage)
Ops | how many personal checks will be done by EIC? (Percentage)
Ops | what will be percentage of telephonic checks will be done by supervisor
Ops | what will be percentage of telephonic checks will be done by EIC
Ops | What is the TAT for QC after it get completed? If interview is done on day 1, by when can will we do QC? Day 2 or 3?
Ops | who will be responsible for meeting QC TAT?
Ops | How do we ensure that EIC is not conducting checks only on supervisors checks and doing fresh checks too
DM/PM/Rese | Who will be doing data QC? | PM
DM/PM/Rese | Who will be responsible for checking answers pattern in data QC | PM
Ops | If there are fraud or any issues in the data, what is the course correction measures we are going to take?
Ops | What is the Condition where we get into 100% checks at interviewer level
Ops | In what scenario, we remove all interviews for an interviewer?
Ops | Team size of audio check team by centre / languages
Ops | What is TAT for checking Audios? If interview is done on day 1, by when can we have Audio report with us? Day 2 or 3?
Ops | How do we ensure tht productivity is maintend as per detailed out in the plan?
Ops | how do we ensure randomness is been maintained in the study?
Ops | how do we ensure skipping pattern in HH is been maintianed?
Qns to be checked at telephonic checks
1. Did the interview happen?
2. Approx length of interview
3. Were the questions read out properly? Was the respondent able to follow and answer?
5. Recruitment Criteria Checked : Category, Brand User, Age, SEC/NCCS
6. Any other feedback from the respondent.
7. Interviewers reading out the options always during each qn consistently?
8. Did the Interviewer have showcards put in front of the respondent during the interview
Ops | Ensure equally checks for all the interviewers?
Ops | what if no check is been done of any interviewers?

## Checks details
Project Name | IRIS 2.0 | Job # | 20221111 | Center | Delhi, Mumbai, Kolkata & Bangalore | FW start date | 2.11.2022 | FW Ended on | 14.11.2022
EIC Name |  | Sup Name |  | Audio checker Name
Repsondent Id | Interviewer name | Accompaniment - Interviewer (Yes/No) | Done by | Int Date | PBC - Interviewer (Yes/No) | Done by | PBC Date | TBC (Yes/No) | Done by | TBS Date | Audio Checks (Yes/No) | Done by | Audio Cheks date
1 | abc | Yes | sup name | 2022-01-01 | NO | - | - | NO | - | - | Yes | Audio Checker Name | 2022-01-03
2 | bcd
3 | cde
4 | def
5 | efg
6 | fgh
7 | ghi
8 | hij
9 | ijk
10 | jkl

## QC requirement at each level
| RQ/listings |  | MQ
QC at EACH STAGE | Supervisor​ | EIC​ | Supervisor​ | EIC​
Accompaniment (AC)​ | 10 | 5 | 10 | 5
Physical Back check (PBC)​ | 30 | 5 | 30 | 5
Telephonic Backchecks | 70 | 5 | 70 | 5
Audio Checks | 30 | 5 | 30 | 5

## SOPs for Adhoc
Ownership | Adhoc/Custom Research - Brand Equity/Communication Research
PM/Res | Explain Sampling Methodolgy - Random or Purposive - Implement the Agreed Methodology | Random
Ops | Prepare a quota sheet of Target Respondents Zonal Representation for recruited respondents Maintain demographic details of respondents recruited with quotas and share
Ops | Validate respondent details considering authentication cards - Such as ID or Product Invoice for ownership
Ops | Ensure the correct respondent profile within defined criteria
Ops | In case of self-administration - respondents' comfort with Internet to be checked
Breifing
Res/PM & Ops | Scripting questionnaire | NA
Res/PM & Ops | Testing of programmed questionnaire | NA
Ops | Receive Scripted version of Research Instrument from Research Team
Ops | Run mock interviews to ensure flow, ask for q're guide in case of complex q're
Ops | As question from research team for any doubt - Attend field briefing by Research and clear doubts
Ops | Make yourself aware about the achievement tracker - Critical for continous tracks
Product Handling
Res/PM & Ops | In case project entails products or simuli, understand operating instruction
Ops | Follow product SoPs as defined by research or client
Ops | Keep cheat sheets or operations manual handy in case of complex electronic products
Fieldwork
Ops | Follow instructions speficied in field briefing note
Ops | Share complexities on day 1 of fieldwork to manage course correction
Ops | Track and monitor progress in MX templates and formats that are defined for field management
Ops | Supervisor to track activity and ensure proper understanding of field teams
Ops | Daily counts of recall interviews conducted with User IDs on daily basis
Ops | Daily upload of the data
Ops | Quotas counts to be shared at the end of FW on daily basis
Ops | Must update on real-time basis in case of any adverse event or product damage
Post-Fieldwork
Ops | Collect/Dispose off the products from the client basis the instruction in FBN
Ops | Pictures of disposed of products to be shared
QC
Ops | Quality norms of 5% accompaniment & 30% back-check to be maintained
Ops | Achievement against expected to be shared with research
Ops | Upload data on central server for QC
Ops | Inform and share the validated data with PM/Research team for monitoring and client management

## Q&A Form_Adhoc
| Adhoc | Responsible Person | TAT to submit | EIC
Recruitment | Is research instrument understanding clear? | Recruitment Supervisor, EIC, PM | Before Placement | Recruitment Supervisor
| Interviewer should be clear of project objectives? Take client on briefing if need be | Recruitment Supervisor, EIC, PM | Before Placement
| Is there a go ahead from teams if not, prepare list of concerns/questions? | Recruitment Supervisor, EIC, PM | Before Placement
| Make a plan to do the booster sample in case of difficult or interlocking quotas? | Recruitment Supervisor, EIC, PM | Before Placement
| Ensure respondents are articulative and can attend interview? | Recruitment Supervisor, EIC, PM | Before Placement
| Is there a record of certificates to authenticate respondent identity? | Recruitment Supervisor, EIC, PM | Before FW
Briefing | Has the breifing done for all interviewers? | Research Manager, EIC, PM | Before FW
| Do all the interviewers understand the flow of the questionnaire? | Research Manager, EIC, PM | Before FW
| Has the mocks calls taken place? | Research Manager, EIC, PM | Before FW
| Who is responsible for the above exercise? | Research Manager, EIC, PM | Before FW
| Has research representative accompanied for Day 1 of fieldwork? | Research Manager, EIC, PM | During FW
Product Handling | Have the detailed counts & pictures of the products shared? | Research Manager, EIC, PM | Before FW
| Explain product usage during field briefing | Research Manager, EIC, PM
| Are instruction per product manual being followed in case any? | Research Manager, EIC, PM
| Are the stimuli or concept card clear for consumers to understand? | Research Manager, EIC, PM
| Do we have the pictures/videos from respondents while using the products? | EIC, PM | To be submitted before Recall
Fieldwork | Measure the expected vs achieved daily achievements… Ensure course correction depending on incidence | Field Supervisor/EIC/PM | Before start of next day's FW
Check if the map and skipping pattern is being followed
Are daily counts from the fieldwork shared?
| Do the counts shared include all the link user IDs? | Field Supervisor/EIC/PM | Before start of next day's FW
| Has the data been uploaded on server today? | Field Supervisor/EIC/PM | On daily basis
| Did we check the quotas from today's fieldwork? | Field Supervisor/EIC/PM | On daily basis
| Did we face any adverse event with the product? Y/N If yes, was it reported within 24 hours? | Field Supervisor/EIC/PM | On daily basis
| Who is responsible for above tasks? | Field Supervisor/EIC/PM | On daily basis
Post-Fieldwork | Ensure to collate the quality sheets | EIC/PM | Within 24 hours of FW Closure
Ensure 30% quality check on the achived sample
| Engage researchers for random quality check for any anomaly. | Research Team
Counts of leftover prodcuts shared?
| Has the left-over products disposed off/submitted back as per the protocols? | EIC/PM | Within 24 hours of FW Closure
QC | Carefully check the QC report, it should be in agreement with the QC norms shared with the client | EIC/PM | Within 24 hours of FW Closure