Project Iris

Field Briefing Note

1st November 2022

| GENERAL | DETAILS | COMMENTS |
| --- | --- | --- |
| Project Details | Version valid since | 10th September 2018 |
|  | Opportunity number | 2817973 |
|  | Project Name | Iris |
|  | Contact Person/Project owners | Akshay Halepaty/ Akshay.halepaty@iqvia.com Anusharth Mulay amulay@in.imshealth.com Nikita Joshi/ nikita.joshi@iqvia.com |
|  | Project Lead | Akshay Halepaty |
|  | Date commissioned | 1st November, 2022 |
|  | Field Team | Shilpa Gupta/shilpa.gupta@market-xcel.com Nahush Kumar/nahush.kumar@market-xcel.com |

| Study Background | Understanding physicians’ perspective on the propositions and identify the most relevant and differentiated communication among gynecologists |
| --- | --- |
| Research Objectives | Feedback on propositions, identify the winning proposition and optimization for release |
| Target Respondent Profile | Gynecologists |
| Key requirements | - Doctors interviewed will be from client database only - Proposition exposure order to be followed as per the center-wise and group-wise quota - Essential to capture the open-ended question for each proposition in exact words as mentioned by the doctor in Q7. While submitting, please ensure key words/ phrases are cleaned and backchecked. Responses like “None”, “Nothing”, etc. will not be accepted - Key questions directly linked to research objectives should be administered with utmost care and probing (wherever required) – Q3, Q5, Q6 and Q11 - No brand names associated with the proposition should be mentioned by the interviewer during the interview, especially during proposition exposure. In addition, no aiding or explanation should be provided to the doctor about the proposition - Quotas should be followed to a 100%. No deviations will be accepted - Similar ratings across propositions will not be accepted unless there is a strong rationale |
| Methodology/ Technique | Quantitative face-to-face CAPI Interviews/ Online telephonic |
| Study Stages | Finalization of Documents: 1st November 2022 Briefing the Field Team: 2nd November 2022 Recruitments and Fieldwork: Start Date – 2nd November 2022; End Date – 14th November 2022 Submission of Raw Data to IQVIA Team: Initial Raw Data for Data Mapping purpose – 7th November 2022 Interim Raw Data at 75% sample size – 9th November 2022 Final Raw Data at 100% sample size – 14th November 2022 Coding, Data Analysis and Processing: 14th to 16th November 2022 |
| Test Location Sample Composition & Quota | As given at the end of the document |
| Materials required for fielding the study | Screener, Questionnaire, Field Briefing Note (FBN), Database, Status Update Sheet, Propositions |
| Field Work Schedule | 2nd November to 14th November 2022 |
| ADR Declaration | Signed by all team members, field team, moderators, and transcribers (Trained by Akshay Halepaty) |
| Key Questions Counter Questions for AE | HIGH PROBABILITY QUESTIONS - NA LOW PROBABILITY QUESTIONS - NA |
| Reporting Timelines | Within 12 hours of conducting the qualitative interview with the doctors |
| IQVIA India PI ADR Reporting Email IDs for Team and Subcontractors | Mail ID: DLI-IQVIA India- PI AE_1@iqvia.com Owner: Rubina Farooqui (owner) Akshay Halepaty (member), Anusharth Mulay (member) Rubina Farooqui (owner) |
| Reconciliation | Once field work begins, you must conduct a reconciliation on monthly basis and at the end of the project on ADR reported to local PV department using the “PV Project Set-up_QC_Reporting Forms and Contact List May 2018”; or ‘client specific PV reconciliation form’ – Even when there is no ADR recorded during the month/ for the project. Reconciliation occurs once a month if the fieldwork is longer than 30 days. Client has the right to audit PV records to confirm compliance with applicable laws. A PV audit may be a documentary audit or otherwise, with client’s auditors or other individuals. Please ensure proper documentation, storage and archiving of related documents. |

SAMPLE SPREAD

| CENTERS | SAMPLE |  | GYNAECOLOGISTS |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | G1 | G2 | G3 | G4 | G5 | T |
| Mumbai | 30 | 6 | 6 | 6 | 6 | 6 | 30 |
| Kolkata | 30 | 6 | 6 | 6 | 6 | 6 | 30 |
| Bangalore | 30 | 6 | 6 | 6 | 6 | 6 | 30 |
| Delhi | 30 | 6 | 6 | 6 | 6 | 6 | 30 |
| TOTAL | 120 | 24 | 24 | 24 | 24 | 24 | 120 |

Details of groups and Order of exposure of propositions to be followed

[City and Group Code should be a part of raw data]

  - Group 1 – ABCDE

  - Group 2 – BCDAE

  - Group 3 – CDABE

  - Group 4 – DABCE

  - Group 5 – EABCD

THANK AND CLOSE